## Cuadro General
Ciclo 1
Phase | Week | General | Actividad | References | Leader | Development | Planning | Quality | Support
LAU | 2 | Project Launch | Organizar primera reunión del equipo | Chapter3 | x
STRAT | 2 | Strategy criteria | Lead the team in stablishing strategy criteria | Chapter 4 |  | x
STRAT | 2 | preliminary estimates | Lead the work to make preliminary size and time stimates | Chapter 4 |  | x
STRAT | 2 | Risk assesment | Lead the team in identifying and assesing project risk | Chapter 4 |  | x
STRAT | 2 | Development strategy | Participate in developing and reviewing the strategy | Chapter 4 | x | x | x | x | x
STRAT | 2 | Configuration control | Participate in reviewing the configuration control process | Appendix B | x | x | x | x | x
STRAT | 2 | Configuration plan | Define the configuration control process | Appendix B |  |  |  |  | x
STRAT | 2 | Document Criteria | Document the selected strategy criteria | Chapter 4 |  |  |  | x
STRAT | 2 | Document Strategy | Document the selected strategy | Chapter 4 |  |  |  | x
PLAN | 2 | Products and sizes | Lead the work to identify the project's products and sizes | Chapter 5 |  |  | x
PLAN | 2 | Task list | Lead the team effort to produce the task list | Chapter 5 |  |  | x
PLAN | 2 | Task hours | Lead the team in estimating the task hours | Chapter 5 |  |  | x
PLAN | 2 | Balance the plan | Lead the team in balancing team workload | Chapter 5 |  |  | x
PLAN | 2 | Weekly hours | Obtain engineers' estimates for their weekly hours | Chapter 5 |  |  | x
PLAN | 2 | Team plan | Produce the preliminary team plan | Chapter 5 |  |  | x
PLAN | 2 | Quality Plan | Participate in making the quality plan | Chapter 5 | x | x | x | x | x
PLAN | 2 | Individual plans | Help each engineer make a personal plan | Chapter 5 |  |  | x
PLAN | 2 | Final plan | Produce final team and individual engineer plans | Chapter 5 |  |  | x
PLAN | 2 | Development plan | Participate in making the development plan | Chapter 5 | x | x |  | x
REQ | 3 | Outline SRS | Lead the team through outlining the SRS | Chapter 6 |  | x
REQ | 3 | System test plan | Lead the team in producing the system test plan | Chapter 9 |  | x
REQ | 3 | Need statement | Participate in analizing and clarifying the requirements | Chapter 6 | x | x | x | x | x
REQ | 3 | Produce SRS | Produce the assigned parts of the SRS | Chapter 6 | x | x | x | x | x
REQ | 3 | System test plan | Participate in producing the system test plan | Chapter 9 | x |  | x | x | x
REQ | 3 | SRS inspection | Participate in inspecting the SRS and system test plan | Appendix C | x | x | x | x | x
REQ | 3 | SRS baseline | When the SRS is corrected, baseline the SRS | Appendix B |  |  |  |  | x
REQ | 3 | Questions | Clarify the need statements with the instructor | Chapter 6 |  | x
REQ | 3 | Final SRS | Obtain updates and produce the final SRS | Chapter 6 |  | x
REQ | 3 | SRS approval | Obtain SRS approval from the instructor | Chapter 6 |  | x
DES | 3 | HDL | Lead the team in producing the high level design | Chapter 7 |  | x
DES | 3 | Produce SDS | Lead the team in producing the SDS | Chapter 7 |  | x
DES | 3 | Design specification | Participate in developing the SDS | Chapter 7 | x |  | x | x | x
DES | 3 | Integration plan | Participate in producing the integration test plan | Chapter 9 | x | x | x | x | x
DES | 3 | SDS inspection | Participate in inspecting the SDS ans integration test plan | Appendix C | x | x | x | x | x
DES | 3 | Final SDS | Obtain update and produce the final SDS | Chapter 7 |  | x
IMP | 4 | Planning | Lead the planning for the implementation work | Chapter 8 |  | x
IMP | 4 | Planning | Participate in planning the implementation work | Chapter 8 | x |  | x | x | x
IMP | 4 | Detailed design | Produce and review detailed designs | Chapter 8 | x | x | x | x | x
IMP | 4 | Unit test plan | Produce and review unit test plans | Script UT | x | x | x | x | x
IMP | 4 | DLD inspection | Participate in inspecting detailed designs and unit teast plans | Appendix C | x | x | x | x | x
IMP | 4 | Test development | Produce unit test materials | Script UT | x | x | x | x | x
IMP | 4 | Implementation | Implement and review programs | Chapter 8 | x | x | x | x | x
IMP | 4 | Compile | Compile programs | Chapter 8 | x | x | x | x | x
IMP | 4 | Code inspection | Participate in inspecting programs | Appendix C | x | x | x | x | x
IMP | 4 | Unit test | Unit test programs | Script UT | x | x | x | x | x
IMP | 4 | Component baseline | When the components are corrected, baseline the components | Appendix B |  |  |  |  | x
TEST | 4 | Test Development | Lead the test development work | Chapter 9 |  | x
TEST | 4 | Build | Lead the work to build the product | Chapter 9 |  | x
TEST | 4 | Integragion | Lead the integration testiong work | Chapter 9 |  | x
TEST | 4 | System test | Lead the system testing of the product | Chapter 9 |  | x
TEST | 4 | User Documentation | Lead the development and review of the documentation | Chapter 9 |  | x
TEST | 4 | Test development | Participate in the test development tasks | Chapter 9 | x |  | x | x | x
TEST | 4 | Build | Participate in building the product | Chapter 9 | x |  | x | x | x
TEST | 4 | Integration | Participate in integrating the product | Chapter 9 | x |  | x | x | x
TEST | 4 | System test | Participate in system-testing the product | Chapter 9 | x |  | x | x | x
TEST | 4 | User documentation | Participate in producing the user documentation | Chapter 9 | x |  | x | x | x
PM | 5 | Cycle report | Participate in reviewing team performance and producing a report on the latest development cycle | Chapter 10 |  |  |  |  | x
PM | 5 | Prepare peer reviews | Complete peer reviews for the support manager's roll and for all the other team roles using form PEER | Chapter 10 |  |  |  |  | x
Every week | - | Data | Obtain the engineer's weekly data | Chapter 5 |  | x | x
Every week | - | Weekly report | Generate the team's WEEK report | Chapter 5 | x |  | x
Every week | - | Weekly analsis | Generar a brief analysis of the performance versus plan | Chapter 5 |  |  | x
Every week | - | Weekly meeting | Participate in the weekly team meeting | Script WEEK |  | x | x | x | x
Every week | - | CCB | Chair the CCB meetings | Appendix B |  |  |  |  | x
Every week | - | Product baseline | Maintain the product baseline | Appendix B |  |  |  |  | x
Every week | - | Manage changes | Manage the change control process | Appendix B |  |  |  |  | x
Every week | - | ITL | Maintain the ITL system and report on risk and issue status | Chapter 15 |  |  |  |  | x
Every week | - | Name glossary | Maintain the system name glossary | Chapter 15 |  |  |  |  | x
Every week | - | Data reporting | Provide agreed weekly data to the planning manager | Chapter 5 |  |  |  |  | x
Every week | - | Instructor reports | Reportar el estado del equipo al instructor | Chapter 11 | x
Every week | - | Tasks and issues | Ayudar el equipo en la asignación de tareas y la solución de hallazgos | Chapter 11 | x
Every week | - | Project notebook | Registro completo de las actividades del grupo en el project notebook | Appendix G | x
Every week | - | CCB | Participate as a member of the configuration control board | Appendix B |  | x
Every week | - | Build control | Ensure that only baselined products are used in build integration and system test of the product | Appendix B |  | x

## Submitable
Script | Week | 1 | n | Submitable
LAU | 1 | x | x | Each student has completed and submitted an INFO form
LAU | 1 | x | x | The development teams are formed and roles assigned
LAU | 1 | x |  | The instructor has described the overall product objectives
LAU | 1 | x |  | The instructor has reviewed and discussed the TSPi and the team's and role goals
LAU | 1 | x | x | The team has agreed on cicle 1 goals, weekly meeting times, and the weekly data to report
STRAT | 2 | x | x | A completed and documented development strategy
STRAT | 2 | x | x | Completed and documented size and time estimated for all product elements to be produced during the next cycle
STRAT | 2 | x | x | Completed and documented estimates for the products to be produced in the subsequent development cycles
STRAT | 2 | x | x | Documented configuration management procedure
STRAT | 2 | x | x | Risks and issues entered in the ITL log
STRAT | 2 | x | x | Conceptual design and completed STRAT form
STRAT | 2 | x | x | Updated project notebook
PLAN | 2 | x | x | Completed team and engineer TASK and SCHEDULE forms
PLAN | 2 | x | x | Completed SUMP, SUMQ, and SUMS forms
PLAN | 2 | x | x | Updated project notebook
REQ | 3 | x | x | A completed and inspected SRS document and system test plan
REQ | 3 | x | x | A completed INS form for the requirements inspection
REQ | 3 | x | x | Time, defect, and size data entered in the TSPi support system
REQ | 3 | x | x | Updated project notebook
DES | 3 | x | x | A completed and inspected SDS and integration test plan
DES | 3 | x |  | The design standards and name glossary
DES | 3 | x | x | Updated SUMP and SUMQ forms and inspection forms
DES | 3 | x | x | Updated project notebook
IMP | 4 | x | x | Completed, inspected, configuration-controlled components
IMP | 4 | x | x | Completed INS forms for the design and code inspections
IMP | 4 | x | x | Unit test plans and support materials
IMP | 4 | x | x | Updated SUMP, SUMQ, SUMS, LOGD, and LOGT forms
IMP | 4 | x | x | Updated project notebook
TEST | 4 | x |  | An integrated and tested cycle-1 product
TEST | 4 | x | x | Completed LOGD and LOGTEST forms for all the test
TEST | 4 | x | x | Completed and reviewed user documentation
TEST | 4 | x | x | Time, size, and defect data entered in the TSPi support system
TEST | 4 |  | x | An integrated and tested cycle-2 or subsequent system
UT |  |  | x | A completed unit test with all defects fixed
UT |  |  | x | Unit test data entered in forms LOGD, LOGT, and LOGTEST
SCM |  |  | x | All products are baselined
SCM |  |  | x | All baseline changes are documented and approved
INS |  |  | x | INS and LOGD forms completed and filed in the project notebook (NOTEBOOK specification in Appendix G)
INS |  |  | x | A fully inspected, high-quality product
PM | 5 | x | x | The development cycle has produced a high-quality product with all required documentation
PM | 5 | x | x | The completed product is under configuration control
PM | 5 | x | x | All process data have been evaluated and PIP's submitted
PM | 5 | x | x | The peer evaluations are done and submitted (PEER)
PM | 5 | x | x | The cycle-1 report has been completed and submitted
PM | 5 | x | x | SUMP and SUMQ forms are completed for the system and all its components
PM | 5 | x | x | The project notebook has been updated
Script Week |  | x | x | The meeting report completed and filed in the project notebook
Script Week |  | x | x | Updated team and engineer TASK, SCHEDULE, WEEK, and CSR forms in the project notebook
Script Week |  | x | x | Updated copy of the ITL log in the project notebook

## Forms
Form | Abbreviation |  | Process Phases
|  | Engineer or Team | LAU | STRAT | PLAN | REQ | DES | IMP | TEST | PM
Configuration Change Request | CCR | E | bar: Process Phases LAU to Process Phases PM
Configuration Status Report | CSR | T | bar: Process Phases STRAT to Process Phases TEST
Student Information Sheet | INFO | E | bar: Process Phases LAU to Process Phases DES
Inspection Report | INS | T | bar: Process Phases STRAT to Process Phases IMP
Issue Tracking Log | ITL | T | [8 empty] | Workbook | bar: Process Phases STRAT to Process Phases TEST
Defect Recording Log | LOGD | E/T | bar: Process Phases LAU to Process Phases PM
Time Recording Log | LOGT | E | bar: Process Phases LAU to Process Phases PM
Test Log | LOGTEST | E | bar: Process Phases STRAT to Process Phases TEST
Team and Peer Evaluation | PEER | E | bar: Process Phases STRAT to Process Phases DES; Process Phases PM
Process Improvement Proposal | PIP | E | bar: Process Phases STRAT to Process Phases PM
Schedule Planning | SCHEDULE | E/T | [8 empty] | Workbook | bar: Process Phases LAU to Process Phases PM
Strategy Recording | STRAT | T | bar: Process Phases STRAT to Process Phases DES
Defects Injected Summary | SUMDI | T | bar: Process Phases STRAT to Process Phases DES
Defects Removed Summary | SUMDR | T | bar: Process Phases STRAT to Process Phases DES
Program Plan Summary | SUMP | E/T | [8 empty] | Workbook | bar: Process Phases LAU to Process Phases PM
Quality Plan | SUMQ | E/T | [8 empty] | Workbook | bar: Process Phases LAU to Process Phases PM
Size Summary | SUMS | E/T | [8 empty] | Workbook | bar: Process Phases LAU to Process Phases PM
Time Summary | SUMT | T
Task Summary | SUMTASK | E
Task Planning | TASK | E/T | [8 empty] | Workbook | bar: Process Phases LAU to Process Phases PM
Weekly Status | WEEK | E/T | bar: Process Phases LAU to Process Phases PM
Note 1: The X means that these forms should be completed in that phase and be available in the team's project notebook the next week.
Note 2: The ? means that these forms may or may not be completed in these phases.
Note 3: E means the form is completed with data for a single engineer, T means the form has data for the team, and E/T means the form is used for both engineer and team data

## Hoja1
SCM
SRS
System Test Plan
Inspección
CCR
SDS

## Test Plan
CPF-01 | Probar EF-1
CPF-02 | Probar EF-2
CPF-03 | Probar EF-3
CPF-04 | Probar EF-4
CPF-05 | Probar EF-5
CPF-06 | Probar EF-6
CPF-07 | Probar EF-7
CPF-08 | Probar EF-8
CPI-01 | Probar Integración